Outline Business Case Guidance

(For approval to procure a LEP to deliver investment in the Secondary School Estate)

Document Status: Issued

April 2007

| Document Properties |  |
| --- | --- |
| Document Author | Technical & Construction Manager |
| Document Owner | Director of Policy & Programme |
| Organisation | Partnerships for Schools |
| Title | Outline Business Case Guidance (For approval to procure a LEP to deliver investment in the Secondary School Estate) |
| Document Type | Guidance |
| Review Date | April 2009 |
| Abstract |  |
| This document provides Local Authorities with guidance on the development of their Outline Business Case for the procurement of a Local Education Partnership to deliver BSF. |  |

TABLE OF CONTENTS

1	EXECUTIVE SUMMARY	4

1.1	Background	4

1.2	The Project	4

1.3	Value for Money	4

1.4	Affordability	4

1.5	Readiness to Deliver	4

1.6	Leading and Managing Change	4

2	BACKGROUND – (Checklist Section A)	5

2.1	The Corporate Vision	5

2.2	Strategic Overview	5

2.3	Key Estate Priorities	5

3	The projectS	6

3.1	Option Analysis & Feasibility – ( Checklist Section B)	6

3.2	Sample Schools – (Checklist Sections B & C)	7

3.3	Sample Schools – Delivery of Strategy for Change – (Checklist Section D)	7

3.4	ICT service provision – (Checklist Sections B,C & D)	8

4	VALUE FOR MONEY – (Checklist Sections E & F)	10

4.1	Summary of Procurement Route for Wave	10

4.2	The PFI Projects	10

4.3	The Conventional D&B Projects	12

4.4	The ICT Project	13

5	AFFORDABILITY – (Checklist Sections F & G)	14

5.1	The PFI Projects	14

5.2	The Conventionally Procured Projects	16

5.3	ICT projects	17

5.4	LEA investment in the LEP	17

5.5	Other sources of funding	17

5.6	Affordability - Concluding Summary	18

5.7	Accounting treatment	18

6	READINESS TO DELIVER  - ( Checklist Section H )	19

6.1	Project Management	19

6.2	Procurement Process	19

6.3	Consultation and Statutory Approvals	19

6.4	Sponsor and School Commitment	20

7	LEADING AND MANAGING CHANGE – (checklist Section H)	21

Appendix 1a: option analysis & FEASIBILITY APPROACH – sample schools	22

Appendix 1B: abnormal costs proforma	23

Appendix 2: sample schools – delivery of strategy for change	24

Appendix 2A: ICT Output specification	25

Appendix 3: Value for money assessment	26

Appendix 4: RISK Matrix – risk Management	28

Appendix 5: UNitary charge model	29

Appendix 6: Funding Allocation Model	30

Appendix 7: AFFordability model	31

APPENDIX 7A: OVERALL FUNDING of BSF	32

Appendix 8: accounting treatment	33

Appendix 9: approvals	34

Appendix 10: DRAFT OJEU	35

Appendix 11: OBC Required KPI Data	36

Appendix 12: Approvals checklist	37

- EXECUTIVE SUMMARY

## Background

This should confirm that there has been no change to corporate, educational or estates strategy since the approval of the Strategy for Change (SfC), and no change to the context or background of the project. If there has been change it should be noted here together with confirmation of approval to the changes.

## The Project

This should summarise the scope of the whole project, together with detail of the sample schemes being put to the market for the procurement i.e.

- Selection of a Local Education Partnership (LEP) Partner to deliver partnering services [insert scope of exclusivity etc];

- Private Finance Initiative (PFI) new build sample project for [insert name of school];

- Design & Build (D&B) refurbishment sample project for [insert name of school];

- ICT services contract [insert scope];

- [Facilities Management (FM) services for D&B ]; and

- [any other services]

## Value for Money

This section should confirm, with reference to the detail set out in the Outline Business Case (OBC) and Appendices, the Value for Money (VFM) rationale for the schemes to be delivered through the Private Finance Initiative.

## Affordability

This section should confirm the affordability of the project scope given the assumptions in this Outline Business Case.

## Readiness to Deliver

This section should summarise the Authority’s organisational structure established to deliver the project, which should also comment on post financial close structures to monitor performance and manage the relationship with the private sector partner.

## Leading and Managing Change

This section should refer back to the strategic overview of the SfC and summarise the Authority’s approach to delivering transformation of educational attainment before, through and beyond the procurement process.

- BACKGROUND – (Checklist Section A)

## The Corporate Vision

This should confirm that the corporate priorities and context as set out in the approved SfC remain valid. Only, if there are any changes or developments to the position stated in the SfC should it be indicated here and detailed in full.

## Strategic Overview

This should confirm that the key strategic objectives as detailed in the strategy for change remain valid and are fully reflected in the OBC proposals. Only if there are any changes or developments to the position stated in the SfC should this be detailed here in full.

Where changes are proposed, the Local Authority (LA) should explain the approvals process and stakeholder consultation process followed to secure buy-in to the changes locally and nationally (DfES, PfS).

## Key Estate Priorities

This should confirm that the position in the SfC for the schools in the wave remains as approved or detail any changes proposed as a result of work towards the OBC which caused there to be a reconsideration, for example changes to proposed scope of works at a school. The summary phasing table taken from the Funding Allocation Model (included in part 2 of the SfC) should be updated and included for reference as Appendix 6.

- The projectS

- Technical Design Guidance, together with advice, support and challenge, will be available from Partnerships for Schools Design Managers to help in the development of this section of the OBC

  - Option Analysis & Feasibility – (Checklist Section B)

- This section should describe a more considered feasibility study for the scope of works at each school as defined at SfC and provide evidence of development to a sufficiently robust level of detail to validate affordability across the wave without pre-empting detailed work by the LEP. This feasibility study may indicate that changes are required to the previous proposals if, with further information, it is found not to offer the most effective solution.

- The appraisal of options at this stage must balance the requirements of the educational strategy (e.g. co-location, disruption to schooling, ICT integration, better circulation) against the need for the proposals for the whole school to be truly deliverable (e.g. affordable, within planning restrictions, suitable ground condition).

- This will involve consideration of the school-specific visions and take account of site constraints such as planning guidance, ground condition, phasing/temporary accommodation, land requirements, access, other abnormals etc. The feasibility study should meet the requirements of Building Bulletin 98 and/or Building Bulletin 77 (where appropriate) and demonstrate for each school:

- How the schools might fit on the site, taking account of community use, access routes, phasing / temporary accommodation, areas of potential expansion;

- A deliverable indicative premises development plan for the whole site; and

- In refurbishment projects, the mix of minor and major refurbishment and new build.

Design Process Protocol

This Design Process Protocol sets out a common process that Local Authorities will need to follow through each stage of their engagement with PfS. Following this protocol will mean that PfS will be able to effectively support design activities and make sure that deliverables will offer the most suitable levels of support to the SfC, OBC and the procurement and operational stages of a project.

The protocol includes design templates. These are provided to help provide a guide to establish a minimum typical content expected for site analysis, option appraisal, control options and for phasing of the SfC and OBC stages. The circumstances of each option may mean that additional information will need to be provided to reassure the Authority, and PfS, that the options across the Wave are affordable. This is particularly the case at OBC, where PfS will also need to have sufficient information to be able to agree the abnormals allocation, and to have confidence that this, together with the authorities design strategy, will deliver the best design quality.

The Design Process Protocol is available on the PfS website:

www.partnershipsforschools.org.uk/design_process.htm

Design Templates

The Design Templates are derived from examples of typical BSF projects in the SfC and OBC stages. They have been chosen as we feel that they exemplify the level of information required for each stage. They are of course provided as guidance, and to assist the authority and their advisors in their own work.

- Templates A  - Tight Urban Site

- Templates B  - Urban Site

- Templates C  - Split Site

Design Quality Indicators for Schools

It is a requirement that all BFS schools should engage with the Design Quality Indicators for Schools (DQIfS) process. During the OBC stage, the Authority should introduce DQIfS to all schools in the wave, but particularly to the sample schools as their DQIfS FAVE report will form part of the output specification in the ITPD stage. Information on the Design Quality Indicators for Schools is available on the Construction Industry Council Website -DQI@CIC.co.uk

  - Sample Schools – (Checklist Sections B & C)

- Sampling Strategy – the authority should outline the rationale for selection of the projects being used to procure the private sector partner. It is envisaged that the sample will include one new build PFI and one D&B refurbishment scheme; an ICT service, possibly an FM contract for non-PFI projects and the LEP partnering services.

- The authority should include the following details for the sample schools at appendix  1:

- School Specific Vision;

- Strategic Brief, including output of the initial DQI stage;

- Drawings showing outcome of feasibility study for each school;

- Costs as prepared by technical advisors; and

- Abnormal costs proforma.

- The authority should also provide confirmation that all schools in the wave have been developed to the same level of detail as the sample schools

  - Sample Schools – Delivery of Strategy for Change – (Checklist Section D)

- The local authority’s Strategy for Change sets out its strategic objectives and plans for improving education provision, highlighting how BSF investment will enable the achievement of these objectives, and the additionality that BSF brings.  In Appendix 2 of the OBC, ‘Sample schools – Delivery of SFC’, the local authority must show how the proposals for each sample school will help deliver these objectives.  In particular:

- In the SfC Part 1 the local authority has set out its authority/area wide objectives and plans in response to key strategic questions (see SfC guidance paragraph 25).  For each sample school the local authority must show how the school’s vision and plans for improvement will help meet these objectives and plans;

- the local authority must show how its plans for each sample school will help  meet the requirements of the remit for the local authority, as set by Ministers, including the specific additionalities that BSF funding should bring;

- In the SfC the local authority has outlined its objectives and plans for each of the key policy areas (see paras 34 – 42 and Appendix 1 of the SfC guidance).  The local authority should show how its plans for each sample school will help deliver these; and

- In the SfC the local authority has outlined its consultation process with schools, and how school visions have been developed.  The local authority should show how the plans for each sample school will ensure that the school’s strategic objectives are met and that outcomes for students will improve.

  - ICT service provision – (Checklist Sections B,C & D)

This section should outline the proposed delivery approach for the ICT provision. This should encapsulate the preferred delivery method and validate the rationale for that choice, including whether the service is only intended to provide for the BSF wave or be applicable to a wider reach.

The purpose of this section is to help define how the ICT solution will meet the objectives of BSF and the vision for ICT stated in the relevant SfC. This section should set out:

- The options that have been considered to deliver ICT within the local BSF project;

- The preferred option and rationale for the choice of this option;

- The scope of services to be included in the ICT provision (e.g. infrastructure, learning platform and operational service); and

- Scalability of the ICT provision, which should include whether it is intended that the service is provided only to the schools included in that BSF Wave, whether it includes other schools in the LA or is applicable to the wider Local Authority.

Creating and reviewing all the ICT options will help stakeholders understand the potential range of solutions that are possible and be clear that the selected service is the most suitable for the circumstances. The output for this section will be very important to support the affordability statements in section 5, which should state the extent to which stakeholders understand and agree to the financial commitments of the proposed provision.

To ensure that the desired ICT solution is closely linked to the objectives of BSF and the vision for ICT stated in the Strategy for Change, the OBC should be accompanied by an ICT Output Specification completed in accordance with the guidance published on the PfS web site. The Output Specification should include Local Authority and School Enhancements referenced back to the LA and school visions. A completed ICT Output Specification will clarify for schools the scope of the managed service which they are signing up to as part of the Affordability process.

The completed ICT Output Specification should be submitted as Appendix 2A of the OBC. An OBC submitted without a satisfactorily completed ICT Output Specification is unlikely to be approved.

The ‘Supplementary OBC ICT Guidance’ should be consulted when completing this section and other relevant sections e.g.  4.4, 5.3, 6.4 and 7. It is available to download from the PfS website in the following zip file: www.partnershipsforschools.org.uk/documents/ICT_Supplementary_OBC_ICT_Guidance_and_Cost_Model.zip

- VALUE FOR MONEY – (Checklist Sections E & F)

This section is based on HMT requirements for approval of funding and is applicable to BSF.

Evidence suggests that PFI offers best Value for Money (VfM) when delivering completely new build schools and a programme level assessment has been made that new build schools will be delivered through PFI contracts.

  - Summary of Procurement Route for Wave

This should set out in tabular form the schools in the wave, the percentage of new build and the choice of procurement route (ie PFI or conventional).

If relevant the Authority should provide the following (with reference back to a Procurement Business Case as appropriate):

- Brief explanation of reasons for not following PFI route for 100% new build schools. (nb this derogation from the BSF assumption of delivery of 100% new build schemes through PFI must have had PfS/DfES approval prior to OBC submission, preferably at the SfC stage).

- Brief explanation for rationale for procurement route for 70-100% new build schools.

- Brief explanation for rationale for not following conventional procurement for 0-70% new build schemes

  - The PFI Projects

    - Qualitative Assessment

This should set out the approach to qualitative VFM assessment as required by the Treasury using the template approach set out in the HMT Value for Money guidance.  LAs are advised to undertake this qualitative VfM assessment on the schools as a single group on the assumption that the risk profiles of each school are broadly similar.

    - Quantitative Assessment

This should set out a confirmation that the Authority has adopted the revised Treasury approach to assessment of quantitative VFM using the Treasury spreadsheet  A link to the latest version of the spreadsheet is included on the PfS Website.

The Authority should provide a separate quantitative VFM for each phase of PFI projects in the wave.

The completed versions should be submitted in Appendix 3 of the OBC.

In Appendix 3 to the OBC, the Authority should also provide a summary of the key inputs to the Treasury spreadsheet with the source of any key assumptions (eg PfS standard assumptions) clearly highlighted.

    - Optimism bias

In this section, the Authority should:

- For pre FBC optimism bias, confirm that the Authority has applied the PfS programme level assumptions in the PFI Quantitative Evaluation Spreadsheet in Appendix 3 Annex 1.  The Authority should explain and justify any divergence from these assumptions if it is considered that there are more appropriate local measures.

- On post FBC optimism bias:

- The Authority and its advisers should refer to the Treasury Value for Money guidance (November 2006) when determining the post FBC optimism bias.

- A brief summary should be included in this section of the methodology and outcomes of the work on determining the post FBC optimism bias.  This should be supported by relevant detailed analysis in Appendix 3.  This analysis should be based on the following steps:

    - Authorities should primarily rely on empirical evidence of a sector specific nature for determining the post FBC optimism bias.

    - To the extent that sector or locally specific empirical evidence/data is not available then authorities should use other sources, such as the Mott MacDonald study detailed in the HMT Green Book.

    - Authorities should undertake analysis to determine whether optimism bias factors obtained from external sources should be mitigated or increased to reflect local and project specific factors.

- Provide a tabular summary of the Pre and Post FBC optimism bias percentages.

    - Summary NPVs and Sensitivity Testing

The Authority should provide the risk adjusted Net Present Value (NPV) of the PFI and PSC and indicate the percentage difference between the two figures ie the Crude PFI VFM figure.

The Authority should undertake sensitivities on the VFM analysis using the Treasury VFM model.  The sensitivities required are set out in the following two tables which should be used to present the results in the OBC.

Table D1 Crude PFI VFM

|  | Crude PFI VFM |
| --- | --- |
| Base Financial VFM Model | % |
| Lifecycle Cost Sensitivity |  |
| -5% | % |
| +5% | % |
| Operating Cost (employment and non-employment) Sensitivity |  |
| -5% | % |
| +5% | % |
| Combined Lifecycle and Operating Cost Sensitivity |  |
| -5% | % |
| +5% | % |

Table D2 Crude PFI VFM

|  | Indifference Point |
| --- | --- |
| Capital Cost Indifference Point | % |
| Unitary Charge Indifference Point | % |

    - Conclusion to PFI VFM Analysis.

The Authority should provide a brief conclusion to the qualitative and quantitative VfM analysis and sensitivities.  It is important that the quantitative analysis is placed in the context of the qualitative analysis.  It should be noted that if the Indifference Points on the sensitivity analysis are less than 5%, then this in itself is not a bar to proving Value for Money.  However in these instances authorities should provide the necessary analytical support (eg strength of underlying assumptions) to support the crude PFI VFM value determined by the VFM spreadsheet.

  - The Conventional D&B Projects

For conventional D&B contracts, authorities will not have to follow the HM Treasury guidance on VFM which is undertaken for PFI projects.

Throughout the procurement process authorities will be expected to ensure that the cost of solutions offered by bidders are ‘on market’ and confirm this as part of the FBC.

  - The ICT Project

As per the VFM assessment on conventional projects, the HM Treasury guidance on VFM is not applicable to ICT contracts in BSF.

Throughout the procurement process authorities will be expected to ensure that the cost of solutions offered by bidders are ‘on market’ and confirm this as part of the FBC.

- AFFORDABILITY – (Checklist Sections F & G)

The following sections require the estimated affordability position for the whole wave to be demonstrated.

Whilst the authority should assess the affordability of the whole BSF project including PFI, conventionally procured projects and the ICT contract, for clarity the OBC should set out the affordability positions of these three different aspects of the project separately.

The followings sections also require authorities to confirm the funding (PFI and conventional) allocated by PfS.  This should reconcile back to the PfS Funding Allocation Model (attached at Appendix 6) and provide confirmation of any agreed exceptional abnormal funding as approved by PfS.

  - The PFI Projects

    - Estimated PFI charges

This section should set out for all PFI projects in the wave, in tabular format, the following information:

| Project | Estimated Financial Close date | Estimated Service start date | Estimated Contract end date | NPV of Unitary Charge (discounted @ 6.0875%) £m | Total Unitary Charge (Nominal) £m | Unitary Charge (indicate price base date) £m |
| --- | --- | --- | --- | --- | --- | --- |
| First phase PFI Project(s) |  |  |  |  |  |  |
| Second phase PFI project(s) etc |  |  |  |  |  |  |

In Appendix 5 to the OBC, the Authority should provide a summary of the key inputs into the shadow unitary charge model with the source of any assumptions (eg PfS standard assumptions) clearly highlighted.  This should cover as a minimum the following:

- Input Costs (capital, lifecycle, hard and soft FM, utilities, insurance, bid costs, SPV management costs/LEP Management Service Fee and relevant proportion of LEP set up costs)

- Funding terms including swap rate

- Investment returns including subordinated debt coupon and blended equity IRR.

- Capital contribution assumptions with justification in light of SoPC3 guidance on capital contributions into PFI schemes.

- Third party income assumptions.

The Authority should provide a summary Sources and Uses of Funds from the shadow unitary charge model.

The Authority should seek advice from their technical and financial advisors in relation to developing the shadow unitary charge model and include the completed model at appendix 5

PfS has developed a simple PFI shadow unitary charge model that provides authorities with a means of estimating a unitary charge for a given set of inputs, the output of which, the profile of the unitary charge, is used in the affordability analysis.  The latest version of this model should be downloaded from the BSF Knowledge Portal.

The model is a conservative shadow bid model and hence provides a prudent estimate of the unitary charge. In most cases the model should prove flexible enough to provide authorities with the confidence at OBC stage of the project’s affordability.  However when finalising the affordability assessment, particularly where there are challenges, authorities are encouraged to liaise with their technical and financial advisers who will be able to undertake, if necessary, a more sophisticated estimate of the Unitary Charge. Please note that there is no obligation to use the simplified model provided by PfS.

    - Estimated PFI credits and Affordability Model.

This section should set out for all PFI projects within the wave:

- The level of credits allocated by PfS based on the allocated funding for the schemes for each Phase. (This will be indicative for non-sample schools as the allocated funding will only be fixed at Stage 1 Approval.  Unless exceptional circumstances apply, the only adjustments to the allocated funding between OBC and Stage 1 approval will be for updated location factors (as published by DfES) and updated forecasts of the DTI PUBSEC index.)

- the PFI Annuity Grant interest rate and scaling factor applied for each of the PFI schemes.  Authorities are asked to refer to the PfS guidance note on PFI credits available on the BSF Knowledge Portal;

- the proposed timing of the draw down of the PFI Annuity Grant.  The PFI Annuity Grant disbursement should be in accordance with the Department for Communities and Local Government guidance on PFI funding and,

- an affordability model to be included in the OBC as Appendix 7.  There is no obligation to use the PfS affordability model, but the Authority should ensure that any model included should contain, as a minimum, the same information as set out in the PfS version.

    - School Contributions

This section should summarise in tabular format for each PFI project the agreed annual contribution from those schools included in the project.

For all schools in the PFI projects in the wave there should be an indicative in principle agreement from governing bodies setting out the contribution required from the schools.  A template letter is included at Appendix 9.

    - Local Authority Contributions

This section should summarise in tabular format for each PFI project the additional authority contribution required in order to meet the affordability gap for the PFI projects.

The Authority should provide a statement to indicate the year on year affordability of the PFI projects. Copies of formal member reports covering the assessment of affordability, together with resolutions approving the budget strategy should be included at Appendix 9 to the OBC.

The Authority should indicate whether any sensitivity analysis has been undertaken on the affordability position.  The Authority should also identify any possible mitigation strategies in the event that the affordability position at financial close for PFI projects differs significantly from that outlined at OBC.

  - The Conventionally Procured Projects

- In Appendix 7 to the OBC, the Authority should provide a summary of the key assumptions in relation to the cost estimates for the conventionally procured projects within the Wave.

    - Capital Cost

- This section should set out in tabular format, on a phase by phase basis, the estimated construction costs including abnormal costs.  The table should also set out the allocated BSF funding from the FAM including the agreed additional abnormal funding.

- The Authority should identify any gap between the estimated cost and agreed funding.  An explanation as to how any funding gap will be met by the Authority should be provided.

- The authority should detail any monies identified by the Authority that might be required to be used in order to share additional costs where the actual cost outturn is above the target cost and is subject to the cost sharing provisions of the D&B contract.

    - Lifecycle/Hard FM costs

This section should set out the costs identified to deliver the lifecycle and hard FM provision for the conventionally funded schools.

The Authority should identify how these costs will be met and how they compare to the current budgeted spend on school maintenance/lifecycle. Any risk monies associated with possible variations from planned maintenance expenditure should be identified.

The Authority should set out the strategy for delivering a common level of maintenance provision across the conventionally funded schools.

For all projects there should be in principle agreement from schools to meeting the required FM/lifecycle expenditure.  Appendix 9 sets out a standard form letter in relation to FM/lifecycle that represents the minimum level of commitment required from governing bodies for the OBC.

  - ICT projects

This section should set out the cost estimates for the ICT solution across the whole wave (or estate) for:

- The indicative capital costs of the selected ICT option;

- monies required to maintain the operational and maintenance (revenue) costs;

- any monies associated with installation and implementation transition; and

- where applicable supplementary costs associated to flexibility and scalability of selected ICT option.

The funding assessment underpinning the ICT cost assumptions of the current project must be set out.

These assumptions should illustrate how the indicative capital costs of the selected ICT option will be met and the means by which the maintenance and lifecycle costs for any ICT works will be afforded. The Authority should provide confirmation that these monies are deliverable and sufficient to maintain the asset for the life cycle of the project.

Appendix 9 sets out a standard form letter which is required to be signed on behalf of governing bodies of all schools in the wave as part of the OBC process.

A spreadsheet template for the ICT funding model can be found within the electronic copy of the Supplementary OBC ICT Guidance document and is available to download from the PfS website in the following zip file: www.partnershipsforschools.org.uk/documents/ICT_Supplementary_OBC_ICT_Guidance_and_Cost_Model.zip. The Authority should customize this to meet its ICT Output Specification and use it to produce its ICT cost estimates.

  - LEA investment in the LEP

In this section the Authority is to confirm:

- The Authority’s acceptance of being an equity partner in the LEP or, where appropriate for non-standard (non-LEP) procurement structures;

- The position of the Authority with respect to investing equity into any PFI holding companies or project companies established for this project;

- The position of the Authority with respect to the desirability of maintaining their share of equity at 10% in the working capital of the LEP over time, or whether the Authority will accept an erosion of their shareholding below 10%; and

- The estimated local authority equity injection, in terms of quantum and timing, arising from the assumptions set out in this section.

  - Other sources of funding

This section should detail any additional central government or other agency funding that is available for this phase of work, the extent to which affordability of the PFI, conventionally procured projects or ICT relies on this funding, and any restrictions or risks associated with securing these monies.  In particular the Authority should set out its strategy for using any land receipts from BSF in accordance with the PfS Funding Guidance document (available on the PfS Website - http://www.partnershipsforschools.org.uk/guidance.htm ).

  - Affordability - Concluding Summary

This section should summarise the overall affordability position for the whole wave taking account of all of sections 5.1 – 5.5 above.  Copies of formal member reports covering the assessment of affordability, together with the resolutions approving the budget strategy should be included at Appendix 9 to the OBC.

  - Accounting treatment

Within the OBC, the authority must conduct an initial qualitative assessment of the likely accounting treatment of the PFI projects.

In particular authorities are expected to have fully developed their demand risk section of the accounting treatment assessment.

The assessment of the demand risk is linked to the development of the SfC and the overall strategy developed to implement education transformation.  It is expected that the SfC process will have helped ensure that the options chosen to deliver the key estate priorities are also appropriate for minimising the demand risk retained by the authority.  It is therefore expected that the demand risk will be lower for a school within a BSF SfC umbrella than a school within a single or grouped school PFI scheme.

The authority should append the results of their own accounting treatment along with evidence of support from their auditor at Appendix 8 of the OBC.

- READINESS TO DELIVER  - ( Checklist Section H )

  - Project Management

This section should set out:

- The project management structure (for example the establishment of a steering group, identification of a project sponsor, programme manager etc) including roles and responsibilities of each part of this structure and how disputes will be managed;

- Resources (internal and external) identified to deliver the project to financial close and through the period of partnership; and

- The approved budgets and the authority to negotiate, delegated powers etc to a named senior officer within the Authority.

  - Procurement Process

This section should set out:

- The expected date of approval to procure from PfS based on the Sample Projects defined in this Outline Business Case;

- The expected date of issuing the OJEU a copy of the draft OJEU document should be included where possible (Appendix 10). This is for approval by PfS and if necessary can be undertaken during the PRG evaluation process;

- The expected timing of the stages of the procurement process; and

- The approach to membership of the selection and evaluation panels.

  - Consultation and Statutory Approvals

This section should set out:

- How the interface with Planning and Highways Officers will be actively managed, ensuring the involvement of key individuals throughout the procurement;

- The level of consultation and approval by SOC where applicable. Full SOC approval, if required, must be secured for all Sample Schemes and evidence included at Appendix 9;

- The stage of planning approval obtained; copies of the outcome of applications should be included at Appendix 9 to this OBC. Ideally Outline Planning consent must be secured for all Sample Schemes before OBC submission and this will be a requirement prior to PfS sign off of ITCD;

- The consultation undertaken with bodies such as Sport England, sports associations / clubs and governing bodies to ensure strategic development of sports facilities across the area; and

- Section 77 applications where required.

  - Sponsor and School Commitment

This section should set out:

- The consultation with stakeholders undertaken in developing the project scope (including identification of which parties have been consulted);and

- Evidence of senior commitment, both strategic (in terms of commitment to the vision and the objectives of this project), and financial, given by the school(s) and the local authority.  This should include commitment to meet operational costs for conventionally funded projects (e.g. ICT).

Copies of resolutions for the Governing Bodies accepting their inclusion into the process, based on the template included at Appendix 9  should be appended to the OBC for all Sample Schemes

- LEADING AND MANAGING CHANGE – (checklist Section H)

- This section should cover how the SfC will be delivered through the implementation of the procurement and prior to and post delivery of the BSF “project”.  Leading and managing change matters because the capital investment in itself will not achieve the SfC objectives. For example the authority might address how cultures and operational processes might be introduced; workforce management, training and recruitment needs; and engagement with schools not in the immediate programme of investment. Consideration should address the following questions:

- For each sample school how will the new school designed for learning in the future translate into the delivery of SfC objectives?  Which objectives will be delivered?  How will staff, parents, pupils and other stakeholders be involved in this process and help to ensure its effectiveness?

- What plans does the local authority have for preparing and training staff for the process of change and transition management?

- How will the local authority maintain existing standards during the period of transition?  What mechanisms are in place to ensure standards are maintained?  What support is available to key school staff as they manage the transition?

- How comprehensive is the risk strategy developed by the local authority in identifying and preparing to manage the educational risks of transition?  Who has been consulted as the educational risk strategy has been developed and are they signed up to the outcomes and responsibilities?

- How have the various stakeholders and community groups been involved in the development of the project scope and implementation strategy for construction project and how will they be engaged in the transformation in education culture and delivery of education outcomes expected pre/post-construction?;

- How complete and effective are the plans to manage:

- internal and external (consulting) resource requirements?;

- interest groups such as governors going forward and mitigating the risk of stakeholder disagreement affecting construction project delivery and transformation?

- the partnership relationship with the LEP – for example establishing non-contractual means by which the partnership can work and how KPIs will be delivered?; and

- local authority involvement (resources) in the LEP including, for example, secondments?

- Appendix 1a: option analysis & FEASIBILITY APPROACH – sample schools

This appendix is to set out the detail of the feasibility studies for each of the sample schools.  This should include annotated drawings and text as required to connect the narrative to each school site proposal.

- Appendix 1B: abnormal costs proforma

The following documents:

- Appendix 1B - OBC Abnormals and external works guidance.doc

- Appendix 1B - OBC Abnormals and external works Proforma.xls

Are available on the PfS website in the following zip file: www.partnershipsforschools.org.uk/documents/OBC Appendices.zip

- Appendix 2: sample schools – delivery of strategy for change

This Appendix should set out how the Authority’s’ Strategy for Change will be delivered for each sample scheme.  This should include annotated drawings and text as required to connect the narrative to the proposals for each school site.

- Appendix 2A: ICT Output specification

The BSF ICT Output Specification Guidance is available on the PfS website:

http://www.partnershipsforschools.org.uk/documents/BSFICTOutputSpecificationGuidanceAugust2006.doc

- Appendix 3: Value for money assessment

The following documents:

- Appendix 3 - VFM Guidance Note and Input Assumptions.doc

- Appendix 3 - PFI Quantitative Evaluation Spreadsheet.zip

Are available on the PfS website in the following zip file: www.partnershipsforschools.org.uk/documents/OBC Appendices.zip

- Appendix 4: RISK Matrix – risk Management

The Risk Matrix appendix is available on the PfS website in the following zip file: www.partnershipsforschools.org.uk/documents/OBC Appendices.zip

- Appendix 5: UNitary charge model

The Authorities should include their unitary charge model. A sample model is available on the PfS website in the following zip file: www.partnershipsforschools.org.uk/documents/OBC Appendices.zip

- Appendix 6: Funding Allocation Model

To be provided by PfS with funding allocation advice, populated by the Local Authority and included here.

- Appendix 7: AFFordability model

The Authority should include the affordability model for the whole wave. The Affordability Model appendix is available on the PfS website in the following zip file: www.partnershipsforschools.org.uk/documents/OBC Appendices.zip

- APPENDIX 7A: OVERALL FUNDING of BSF

The Funding envelope is available on the PfS website in the following zip file: www.partnershipsforschools.org.uk/documents/OBC Appendices.zip

- Appendix 8: accounting treatment

The authority should append the results of their own accounting treatment along with evidence of support from their auditor here.

- Appendix 9: approvals

The Local Authority should insert here all the evidence needed to demonstrate that appropriate approvals have been secured for the relevant schools. For example:

- Committee reports on affordability

- GB resolutions

- Planning advice and permissions

- SOC approvals

- Section 77 approvals

- Any other approvals as considered necessary

The following documents:

- Appendix 9 - Governing Body Specimen Resolution for PFI contributions.doc

- Appendix 9 - OBC ICT Letter.doc

- Appendix 9 - PfS Example OBC FM and lifecycle letter.doc

- Appendix 9 - Points to be covered by s151 Officer Letter.doc

Are available on the PfS website in the following zip file: www.partnershipsforschools.org.uk/documents/OBC Appendices.zip

- Appendix 10: DRAFT OJEU

A template BSF OJEU can be obtained from the PfS website at the following location:

www.partnershipsforschools.org.uk/StandardDocumentList.htm#pd

# Appendix 11: OBC Required KPI Data

The OBC Required KPI data appendix is available on the PfS website in the following zip file: www.partnershipsforschools.org.uk/documents/OBC Appendices.zip

- Appendix 12: Approvals checklist

Note: This checklist is for information only – it is not to be completed by the Authority or its Advisors.

An example OBC checklist is available on the PfS website in the following zip file: www.partnershipsforschools.org.uk/documents/OBC Appendices.zip